Logistics
or
Making it Happen

---
Soon	Reserve housing & parking / Reserve venue / Administrative support
February	Determine selection criteria / Create application form / Publicize event
March	Draft agenda / Invite speakers
April	Create attendee requirements form / Select attendees
(Varies)	Confirm reservations / Arrange meals
May	Coordinate with speakers
June	Finalize agenda / Attend UVa Tapestry

---
A.S.A.P.: Reserve Space
- Reserve housing & parking
  - Single block of rooms
  - Internet connectivity
- Reserve venue
  - Tables, collaboration space, projector screen
  - Electricity for 30 laptops
- Keep venue, housing, and dining close together
- Seek support
  - Let deans, chairs, etc., know this is in the works
  - Can you get secretarial aid?

---
February: Prepare Applications
- Selection criteria
  - Ask questions that help you choose
  - Our criteria work well for us…
    - Are they teaching CS? How long?
    - Can they demonstrate interest in diversity?
- Create application form
  - Web-form
  - Verify important information
  - Both current and summer contact information
- Check with us to avoid multiple-venue acceptances

---
February–April: Recruiting
- We send joint announcements to SIGCSE, CSTA
  - Announcement going out soon
  - Let us know how much to say
- Mailing lists from
  - School districts
  - Professors in education department
- Word of mouth

---
March: Invite Speakers
- Draft agenda
  - What to cover, not necessarily when
- Invite speakers
  - Applicability of topics
  - Demographic spread
  - Teaching ability
  - Attitude toward high school, diversity
  - Evidence, not just anecdote
  - Cost

---
April: Attendee Selection
- Create attendee requirements form
  - Accessibility needs
  - Food needs/allergies
  - Housing requirements
    - Some choose not to use provided housing
  - Paper or digital handouts
- Select attendees
  - Delay telling “wait list” candidates
  - Encourage reapplying next year

---
(Varies): Meeting Logistics
- Confirm reservations
  - Release unneeded housing, parking, etc.
  - Accommodate accessibility needs
- Arrange meals
  - You should eat with participants
  - Speakers often stay for at least one meal
  - Beverages all day (hot and cold)
  - Some food between meals
- Invite visitors (deans, etc.)

---
May: Coordinate with Speakers
- Transportation, hotel reservations, etc.
- Orient the speakers
  - Presentation style
    - Interactive, directly applicable
    - 1 hour, ≤ 20 minutes of that spent talking
    - Anecdote, evidence, & interaction
  - Their audience
    - Teachers: they like to talk
    - The best: bright, energetic, enthusiastic
    - Overworked: ideas need concrete application
    - Fighting several fronts
    - Assume no formal CS background

---
June–July: “Finalize” Agenda
- Order NCWIT handouts (allow 6 weeks delivery)
  - We’ll also bring some
- UVa Tapestry (funded organizers; June 25–27)
  - See a workshop in action
- Think about
  - Speaker schedules
  - Variety, flow, breaks, social time
  - Distributing & collecting room keys, per diem checks
  - Orientation (locations, Internet passcodes, etc.)
- Leave luncheon unstructured
- Last-minute changes do happen

---
Questions?
November	Reserve housing & parking / Reserve venue / Administrative support
February	Determine selection criteria / Create application form / Publicize event
March	Draft agenda / Invite speakers
April	Create attendee requirements form / Select attendees
(Varies)	Confirm reservations / Arrange meals
May	Coordinate with speakers
June	Finalize agenda / Attend UVa Tapestry
July	Hold workshop!